Phase 0 — Freeze the scope now

Core question

Your repo should answer one question only:

Does biologically structured ranking improve prioritization of candidate regulatory links over standard correlation-based ranking?

That matches what your current pipeline already does: baseline candidate generation with LinkPeaks(), followed by additive vs multiplicative vs distance-aware reranking.

Do not expand scope yet

For now, SKIP:

- Hi-C

- learned weights

- general N-omics framework

- fancy model language

- “causal” claims

Those are phase-2 or phase-3 problems.

Phase 1 — Finish the toy properly

Timebox

1–2 weeks max

Not longer.

If you are still tuning toy data after 2 weeks, you are avoiding the real work.

Goal

Use the toy/pilot only to settle:

- scoring structure

- output objects

- comparison metrics

- plotting/report format

Not to prove the whole paper.

What to include in the toy

Use only:

- RNA

- ATAC

- distance

- motif

Optional later in toy:

- reproducibility, only if you already have donor structure

- footprint, only if motif integration is already stable

What to exclude in the toy for now

SKIP initially:

- footprint

- reproducibility

- anything requiring heavy external preprocessing

- benchmark against 5 tools

- raw-data generalization

Why

Your current pilot already shows the main signal: multiplicative + soft distance prior changes the ranking and improves downstream enrichment.

That is enough to define the skeleton.

Phase 2 — Lock the scoring architecture before repo build

Do this before you touch raw-data workflow engineering.

Final v1 score structure

Use this logic:

Core

RNA × ATAC

This is your main signal.

Soft modifiers

- distance

- motif

- later reproducibility

- later footprint

So structurally:

score = core × soft_modifiers

Not a flat weighted soup.

Why

This avoids arbitrary weight chaos.

Do not start with:

w1*RNA + w2*ATAC + w3*motif + w4*distance + w5*footprint

That will explode immediately.

Recommended v1 formula family

Something like:

score = core_signal × distance_modifier × motif_modifier

where:

- core_signal = f(RNA, ATAC)

- distance_modifier = 1 - λd + λd * D

- motif_modifier = 1 - λm + λm * M

This means:

- if motif or distance is weak, score is reduced

- but not zeroed out

- modifiers are interpretable

- each λ is bounded in [0,1]

That is much cleaner than unconstrained weights.

Phase 3 — Weight handling so it does not become arbitrary nonsense

This is the main part.

Immediate answer

Do not solve “true weights” first.

Do this instead:

Step 1

Normalize every component onto a comparable range:

- 0–1

- percentile

- empirical CDF

- bounded z-derived transform

Step 2

Use bounded modifier strengths

- λd ∈ {0.1, 0.2, 0.3}

- λm ∈ {0.1, 0.2, 0.3}

- later λr, λf

Step 3

Run a small grid, not open-ended tuning

Example grid:

- distance modifier: 0.1 / 0.2 / 0.3

- motif modifier: 0 / 0.1 / 0.2 / 0.3

That is enough.

Selection criterion

Choose weights by:

- rank stability

- ORA consistency

- gene diversity

- transfer across datasets

Not by “this one looks biologically nicest.”

Rule

A weight setting is accepted only if:

- it improves over baseline

- it is not the only setting that works

- nearby settings behave similarly

That is your anti-explosion rule.

What to report later

Not “we chose 0.2 because it felt right.”

Instead:

We evaluated a constrained parameter grid and selected settings that were stable across resampling and yielded consistent improvements across datasets.

That is the defensible version.

Phase 4 — When to stop playing and start from raw data

Trigger

You move from toy to raw as soon as these 4 are true:

1

You know the v1 score structure
Example:

- core = RNA × ATAC

- distance = soft prior

- motif = soft gate

2

You know the v1 outputs

- ranked links table

- top-N comparison

- overlap stats

- ORA

- distance distribution

- promoted/demoted links

3

You know the v1 metrics

- top-N overlap with baseline/tool

- gene diversity

- ORA coherence

- distal fraction

- rank stability

4

You have a fixed small parameter grid

Once these are defined, stop toy work.

At that point, the raw-data repo build starts.

Practical timing

That should happen after 1–2 weeks, not months.

Phase 5 — Repo build order

Build the repo around the workflow you already understand from your PBMC repo: structured preprocessing, scoring, evaluation, and report generation.

Build order

Stage A — minimal repo skeleton

Create:

- config/

- workflow/

- scripts/

- containers/

- docs/

- results/ or examples/

Do this before full benchmark expansion.

Stage B — raw-data workflow

Support one dataset end-to-end:

- raw 10x multiome input

- object build

- baseline candidate generation

- reranking

- evaluation

- figures

Stage C — second dataset

Only after dataset 1 runs cleanly.

Stage D — benchmarking module

Only after your own pipeline is stable.

Phase 6 — Feature order: what to include and when

This is the sequence.

v1 method

INCLUDE

- RNA

- ATAC

- distance

- motif

SKIP

- footprint

- reproducibility

Why:

- RNA + ATAC + distance already works in your pilot

- motif is the next logical, low-complexity biological addition

- footprint and reproducibility add complexity and extra failure modes

v1.5

ADD

- reproducibility

Only if you have donor-aware or replicate-aware data.

Use reproducibility as:

- a modifier

- or a confidence label

Not as a giant competing term.

Example:
final = score × reproducibility_modifier

Good use:

- penalize dataset-specific junk

- reward consistent links

Bad use:

- make it dominate all rankings

v2

ADD

- footprint

Only after motif works.

Reason:
footprint without motif is noisy, and footprint integration is harder to stabilize.

So order is:

- motif

- reproducibility

- footprint

Not the other way around.

Phase 7 — Benchmarking: when to start and what to include

When

Start benchmarking after raw-data v1 is running on one dataset.

Do not benchmark while the core score is still changing every day.

Benchmark order

First benchmark set

- Signac LinkPeaks

- your additive

- your multiplicative

- your final v1

This is internal benchmarking.

Second benchmark set

Add external tools:

- ArchR peak2gene

- Cicero

That is enough for a serious first pass.

Optional later

- GLUE

- MultiVI

- other deep methods

Only if they clearly fit the same task.

Do not benchmark against methods that solve a different problem just to inflate the table.

Phase 8 — Minimal benchmark metrics

Do not overcomplicate this.

Must-have metrics

Ranking behavior

- top-N overlap

- promoted vs demoted links

- rank correlation

Biological coherence

- ORA / pathway enrichment

- term consistency across runs

Diversity

- unique genes in top N

- concentration of top links per gene

Distance behavior

- median distance of top links

- fraction of distal links

- does distal recovery destroy enrichment?

Stability

- subsampling

- donor splits if possible

Best external metric if available

- overlap with known enhancer–gene references

- validated regulatory links

- promoter capture / CRISPR resources

But that is bonus, not v1 requirement.

Phase 9 — Exact work plan

Week 1

Goal

Finish toy and freeze v1 design

Tasks

- freeze v1 score family

- add motif as soft modifier

- run small parameter grid

- choose fixed output plots/tables

- define benchmark metrics

Deliverable

One short internal methods note:

- score definition

- parameter grid

- metrics

- output schema

If you cannot write that note, the method is still too vague.

Week 2

Goal

Start repo and raw-data pipeline

Tasks

- create new repo

- copy engineering skeleton style from old repo

- implement one raw 10x multiome dataset end-to-end

- baseline + your v1 score

- generate standard outputs

Deliverable

A reproducible run from raw input to ranked links and figures

Week 3

Goal

Stabilize and test

Tasks

- run second dataset

- add sensitivity analysis

- lock default parameters

- write benchmark wrappers for ArchR/Cicero or prepare inputs

Deliverable

Dataset 1 + dataset 2 comparable outputs

Week 4+

Goal

Benchmark seriously

Tasks

- external tool comparisons

- rank and ORA comparison

- stability/subsampling

- draft figure set

Deliverable

Enough material to judge preprint viability

Decision rules so this does not spiral

Rule 1

No new signal type until current one improves something measurable.

Example:

- motif gets added only if it improves ranking behavior or biological coherence

- otherwise it stays optional

Rule 2

No new tool benchmark until your own pipeline is stable on 2 datasets.

Rule 3

No learned weights until fixed-structure scoring is reproducible.

Rule 4

No footprint until motif integration is settled.

Rule 5

No third omics layer before v1 benchmark is complete.

These rules matter.

Final recommendation for components

v1 include

APPLY

- RNA

- ATAC

- distance

- motif

v1 optional

LATER

- reproducibility

v2

LATER

- footprint

v3

LATER

- Hi-C / third omics

Final recommendation for weights

For now

APPLY

- bounded soft modifiers

- small parameter grid

- choose by stability + coherence

Do not do now

SKIP

- free-form weighted sums

- neural-network weighting

- dataset-specific manual tuning

- many unconstrained knobs

If you want the shortest version

Stop toy after:

- score structure fixed

- outputs fixed

- metrics fixed

- small weight grid fixed

Build repo when:

- motif soft gate is decided

- one v1 formula family is locked

Include first:

- RNA

- ATAC

- distance

- motif

Add later:

- reproducibility

- footprint

Benchmark when:

- raw-data pipeline runs on one dataset cleanly

Preprint threshold:

- works on at least 2 datasets

- benchmarked against LinkPeaks + ArchR/Cicero

- stable across nearby weights

That is the plan that does not explode.

Top of Form

Bottom of Form